## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-04-d-td
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | SA; 10/20/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | SA; 10/20/18
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | SA; 10/20/18
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | SA; 10/20/18
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | SA; 10/20/18
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | SA; 10/20/18
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | SA; 10/20/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | SA; 10/20/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | SA; 10/20/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  |  |  | RV; 10/28/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  |  |  | RV; 10/28/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  |  |  | RV; 10/28/18
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  |  |  | RV; 10/28/18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  |  | RV; 10/28/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  |  | RV; 10/28/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  |  | RV; 10/28/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  |  |  | RV; 10/28/18
As a player I want to move first if my checkers are red in color so that I can play a game of checkers according to American Rules. | Given I'm the red player when Its the first turn of the game and I try to move then the turn is completed. |  |  |  | BP; 11/04/18
| Given I'm the white player when it's the first turn of the game and I try to move then an error message is displayed saying it's not my turn |  |  |  | BP; 11/04/18
As a player I want to move every turn so that I do don’t lose the game. | Given it's my turn when I try to make a valid move then the move is executed | [5 empty] | RV; 11/25/18
| Given it's my turn when I cannot move any of my remaining pieces then I lose the game | [5 empty] | RV; 11/25/18
| Given it's my turn when I have possible moves I can make then the game will not continue until I make a move | [5 empty] | RV; 11/25/18
| Given it's not my turn when I'm in a game then wait until it is my turn | [5 empty] | RV; 11/25/18
As a player I want to move diagonally forward to a vacant dark square so I can get in position to jump an enemy checker or reach the king row. | Given it's the player's turn when the player drops a piece to an adjacent, dark square thats not occupied then then the move is completed. | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player drops a piece on an invalid square then the move is not completed and an error message is displayed | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player makes a move then the board displays the changes to both users | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player makes a move then the player may not move his piece again before submitting his turn | [5 empty] | RV; 11/25/18
As a player I want to reach the row furthest from me so I can create a king checker piece and move both forwards and backwards diagonally | Given it's the player's turn when the player reaches the farthest opposite row then the player's piece will become a king Piece | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player attempts to move their king piece then the piece will be able to move in any direction to a diagonal dark square. | [5 empty] | RV; 11/25/18
As a player I want to capture an opponent’s piece by jumping over it, diagonally, to an adjacent vacant dark square so I can become one step closer to winning the game. | Given it's the player's turn when the player makes a valid jump over an opponent then the turn is completed. | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player makes a valid jump over an opponent and the piece is dropped then the opponents piece is removed from the board. | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player makes a invalid jump over an opponent then the jump will not be completed and it will still be the player's turn | [5 empty] | RV; 11/25/18
As a player I want to make a multiple jump move from vacant dark square to vacant dark square, capturing one of the opponent’s pieces with each jump, so that I can become closer to winning the game. | Given it's the player's turn when the player makes a jump move and has one additional jump available then the player makes the jump over their opponent's' piece. | [5 empty] | RV; 11/25/18
| Given it's the player's turn when the player makes a jump move and has another jump available then the player must complete the jump before submitting turn | [5 empty] | RV; 11/25/18
As a player I want to resign from a game so I don’t have to play until the end. | Given a player wants to quit when the player clicks Sign out [ playerName ] then the opponent is notified. | [5 empty] | SA; 11/25/18
| Given a player wants to quit when the player clicks Sign out [ playerName ] then the game ends | [5 empty] | SA; 11/25/18
| Given a player wants to quit when the player clicks Sign out [ playerName ] then player stats are updated | [5 empty] | SA; 11/25/18
| Given a player wants to quit when the player clicks Sign out [ playerName ] then the game is removed from Game Services | [5 empty] | SA; 11/25/18
| Given a player wants to quit when the player clicks Sign out [ playerName ] then both players are brought back to the home screen | [5 empty] | SA; 11/25/18
As a Player making a move, I want to be able to undo a piece placement before submission, so that i can undo my mistake and continue thinking. | Given I'm a player who made a piece movement when I click the back up option then I expect my piece movement to be back where it was. | [5 empty] | SA; 11/25/18. pending move wasn’t being removed, causing the program to believe the move was already made when a player tried to move his piece again after doing a back up. Fixed.
y r u here